## Epics
Epic ID | Name | Cognitive Verb | Description | Priority | Status | Stories
E01 | Orchestration & Heartbeat | cross-cutting | Stand up OpenClaw as a persistent daemon with heartbeat scheduler and basic I/O channel. | P0 | Todo | 5
E02 | Memory Substrate | cross-cutting | Deploy MemOS with Qdrant + Kuzu backends. Wire the OpenClaw plugin for pre/post-turn recall and capture. | P0 | Todo | 6
E03 | Skill Runtime | cross-cutting | Integrate OpenSpace as an MCP server. Enable skill discovery, loading, and invocation from OpenClaw. | P0 | Todo | 4
E04 | Curation Policy | curate | Salience scoring, deduplication, and contradiction detection at memory write time. | P0 | Todo | 5
E05 | Rewire Policy | rewire | Knowledge graph maintenance in Kuzu. Edge creation, contradiction resolution with supersession. | P0 | Todo | 5
E06 | Reflection Policy | refine | Heartbeat-driven review of recent episodes and skill invocations. Insight extraction, skill quality updates. | P0 | Todo | 4
E07 | Consolidation Policy | learn | Nightly episodic-to-semantic consolidation. The sleep analog. | P0 | Todo | 4
E08 | Pruning Policy | unlearn | Decay scoring, memory deletion, orphan edge cleanup. Weekly pass. | P0 | Todo | 4
E09 | Unlearn on Demand | unlearn | User-triggered or policy-triggered deletion with cascade and tombstones. | P1 | Todo | 3
E10 | Skill Creation Policy | create | Auto-generate skills from successfully-completed novel tasks. Self-verification before library add. | P1 | Todo | 4
E11 | Observability | cross-cutting | Structured logs for every policy firing. Memory inspector CLI. | P1 | Todo | 3
E12 | Hyperscaler Deployment | cross-cutting | Move from local Docker Compose to AWS/GCP/Azure. IaC, secrets, TLS. | P2 | Todo | 5
E13 | Parametric Learning | learn | Periodic LoRA fine-tuning on consolidated high-confidence knowledge. Research / experimental. | P2 | Todo | 4

## Stories
Story ID | Epic | Title | As a... | I want... | So that... | Acceptance Criteria | Est (d) | Status
S001 | E01 | Run OpenClaw locally | developer | to run OpenClaw on my machine via Docker | I can iterate on the agent loop without a VPS | Container starts cleanly; daemon survives restart; openclaw CLI responds to ping. | 1 | Todo
S002 | E01 | CLI channel | user | to talk to the agent via a CLI | I can test turns without setting up Telegram | I can send text, receive response; session persists across commands. | 1 | Todo
S003 | E01 | Heartbeat scheduler | system | heartbeat jobs to fire on cron schedules | policies run without my intervention | Minimum three schedules (30m, daily, weekly) each invoke a test skill reliably. | 2 | Todo
S004 | E01 | Structured logging | operator | every turn and heartbeat firing to be logged with context | I can debug and audit behavior | JSON log lines with trace_id, policy, duration, outcome. | 1 | Todo
S005 | E01 | Config from env | developer | OpenClaw to load all config from .env | no secrets in code; env-driven deployments | .env.example documents every var; missing vars fail fast with a clear error. | 1 | Todo
S006 | E02 | Deploy Qdrant | system | Qdrant to be available as a Docker service | MemOS has a vector backend | Qdrant reachable on internal network; collection created on startup. | 1 | Todo
S007 | E02 | Deploy Kuzu | system | Kuzu to be available as embedded graph DB | MemOS has a graph backend | Kuzu DB file created; basic node/edge round-trip works. | 1 | Todo
S008 | E02 | Deploy MemOS | system | MemOS to run with Qdrant+Kuzu config | the agent has unified memory API | MemOS API responds to add/get/search/delete against both backends. | 2 | Todo
S009 | E02 | OpenClaw MemOS plugin | system | the official plugin installed and active | memory recall+capture happens automatically per turn | Pre-turn context includes ≥1 relevant memory when history exists; post-turn writes confirmed. | 1 | Todo
S010 | E02 | Memory inspector CLI | developer | a command to dump recent memories | I can verify writes and debug | `python -m src.core.inspect memories --last 20` prints recent entries. | 1 | Todo
S011 | E02 | Seed test memories | developer | a script to load fixture memories | I can test retrieval and policies deterministically | Script inserts ≥50 episodic and 10 semantic memories with known content. | 1 | Todo
S012 | E03 | Install OpenSpace | system | OpenSpace running as MCP server | skills can be loaded and invoked | OpenSpace MCP registered with OpenClaw; `skills list` returns stub skills. | 1 | Todo
S013 | E03 | Skills directory convention | developer | skills/ folder to be the canonical skill location | skills live in git alongside code | OPENSPACE_HOST_SKILL_DIRS points to ./skills; new SKILL.md is discovered without restart. | 1 | Todo
S014 | E03 | Policy skill template | developer | a SKILL.md template for cognitive policies | all six policies have a consistent shape | Template used by all policy SKILL.md files; includes triggers, inputs, outputs, logging. | 1 | Todo
S015 | E03 | Verify skill invocation | developer | to manually invoke a skill and see output | I can test without full agent loop | `openspace invoke <name>` runs a skill end-to-end with mock context. | 1 | Todo
S016 | E04 | Salience score function | system | every memory candidate to get a 0-1 salience score | low-value memories don't pollute storage | Score considers recency, repetition, entity density, user marker; unit tested. | 2 | Todo
S017 | E04 | Threshold-gated writes | system | writes below threshold to be rejected | storage stays clean | Default threshold 0.3; rejections logged with reason; overridable per call. | 1 | Todo
S018 | E04 | Near-duplicate detection | system | similar memories to be merged rather than duplicated | no noise accumulation | Cosine similarity > 0.92 against existing memory triggers merge, not insert. | 2 | Todo
S019 | E04 | Contradiction flag | system | conflicting facts to be detected at write time | rewire policy can act on them | Claude-based entailment check; conflicts emit an event the rewire policy consumes. | 3 | Todo
S020 | E04 | User override: remember this | user | a way to bypass curation when I say 'remember this' | important things aren't filtered | Explicit marker sets salience to 1.0; still deduplicated. | 1 | Todo
S021 | E05 | Entity extraction | system | entities extracted from each episode | the graph has nodes to connect | Claude-based NER extracts named entities; stored as Kuzu nodes. | 2 | Todo
S022 | E05 | Co-occurrence edges | system | edges added when entities co-occur in an episode | relationships form organically | Edge created with source=episode_id, weight=frequency. | 1 | Todo
S023 | E05 | Supersession on contradiction | system | superseded facts retained but marked | history is preserved | Old fact gets status='superseded', link to new fact; retrieval default hides superseded. | 2 | Todo
S024 | E05 | Orphan cleanup | system | nodes with zero edges to be removed on pruning | graph stays lean | Orphans older than N days are deleted; deletion logged. | 1 | Todo
S025 | E05 | Path-based 'why' query | user | to ask why two facts are linked | I can debug the graph | CLI: `why A B` prints shortest path with edge provenance. | 2 | Todo
S026 | E06 | Skill invocation tracking | system | every skill call to record outcome | quality can be scored | Logs: success, failure_type, user_correction, duration. | 1 | Todo
S027 | E06 | Skill quality score | system | each skill to have a rolling quality score | reflection can act on it | EWMA over last 20 invocations; score updates after each call. | 1 | Todo
S028 | E06 | Insight extraction | system | heartbeat to extract insights from recent episodes | patterns surface | Every 30m: sample last N episodes, ask Claude for patterns, write to semantic memory. | 2 | Todo
S029 | E06 | Deprecate failing skills | system | consistently-failing skills to be deprecated | library stays healthy | Skill with quality < 0.3 over 10 invocations gets status='deprecated'; no retrieval. | 1 | Todo
S030 | E07 | Daily consolidation job | system | a nightly job that summarizes yesterday's episodes | semantic memory grows | Fires at 03:00; writes N semantic entries; original episodes tagged 'consolidated'. | 2 | Todo
S031 | E07 | Confidence scoring | system | semantic memories to carry confidence | downstream can filter | Score based on episode count, user corrections, recency; stored with memory. | 1 | Todo
S032 | E07 | Long-term tier promotion | system | high-confidence semantic memories to move to always-retrievable tier | core knowledge is sticky | Confidence > 0.8 and age > 14d → promoted; promoted memories bypass decay. | 2 | Todo
S033 | E07 | Snapshot export | user | to export all consolidated knowledge | I can back up my agent's mind | CLI: `export snapshot --out file.json`; round-trip import preserves content. | 2 | Todo
S034 | E08 | Decay scoring | system | every memory to have a decay score that grows with age and disuse | pruning has a signal | Score = f(age, last_access, confidence); updated on each access. | 1 | Todo
S035 | E08 | Weekly pruning pass | system | a job that deletes memories below threshold | storage stays bounded | Sundays at 03:30; deletes items with decay > threshold and not promoted. | 2 | Todo
S036 | E08 | Cascade graph cleanup | system | deletions to cascade to graph edges | no dangling references | On memory delete: remove edges referencing it; remove orphan nodes. | 1 | Todo
S037 | E08 | Deletion audit log | operator | every deletion to be logged | I can recover within grace window | Log entry includes memory_id, reason, timestamp, 7-day grace window. | 1 | Todo
S038 | E09 | User forget command | user | to say 'forget X' and have it removed | I control my agent's memory | CLI and chat both support: `forget <topic¦entity¦time-range>`; confirmation required. | 2 | Todo
S039 | E09 | Tombstones | system | deleted items to leave a tombstone | superseded retrieval still works | Tombstone records deletion_reason and supersedes_id; retrievable by ID, not search. | 1 | Todo
S040 | E09 | Recovery from audit log | operator | to restore a recently-deleted item | accidental deletions are recoverable | CLI: `undelete <id>` within 7-day grace window restores with original metadata. | 1 | Todo
S041 | E10 | Novel-task detection | system | to detect when a completed task has no matching skill | create policy knows when to fire | After successful turn: embedding match against skill library; below threshold → novel. | 2 | Todo
S042 | E10 | Skill generation | system | to generate a SKILL.md and code from a successful trajectory | skills accumulate automatically | Claude-generated skill; passes lint and unit-test template; added to draft state. | 3 | Todo
S043 | E10 | Self-verification | system | generated skills to prove themselves before promotion | quality bar enforced | Skill must succeed on 2 held-out synthetic cases; otherwise stays in draft. | 2 | Todo
S044 | E10 | Skill naming + dedup | system | to avoid creating near-duplicate skills | library stays crisp | Embedding match against existing skills > 0.88 → propose merge instead of new. | 1 | Todo
S045 | E11 | Policy firing log | operator | every policy firing to emit a structured log | I can see what the agent is doing | JSON lines: policy, trigger, inputs_summary, effect, duration, outcome. | 1 | Todo
S046 | E11 | Memory inspector UI | developer | a simple web UI to browse memories and graph | faster debugging than CLI | FastAPI + minimal HTML; read-only; lists, searches, shows graph neighborhood. | 3 | Todo
S047 | E11 | Health check endpoint | operator | a /healthz endpoint | standard monitoring works | Returns 200 when all L1-L3 services reachable; 503 otherwise. | 1 | Todo
S048 | E12 | Pick hyperscaler | architect | to choose AWS, GCP, or Azure | IaC can target one | Decision recorded in docs with tradeoffs. | 0.5 | Todo
S049 | E12 | IaC skeleton | architect | Terraform or equivalent to define the environment | environments are reproducible | One-command `terraform apply` brings up VM, volumes, security group. | 3 | Todo
S050 | E12 | Secret management | operator | secrets to live in the hyperscaler's vault | no secrets on disk | .env replaced by managed secret references at runtime. | 2 | Todo
S051 | E12 | TLS everywhere | operator | all services to speak TLS | production-grade network security | Reverse proxy (Caddy) terminates TLS; internal traffic via mTLS or private net. | 2 | Todo
S052 | E12 | Automated backups | operator | Qdrant+Kuzu+SQLite to be backed up nightly | disaster recovery works | Snapshot script runs via cron; restored on a fresh host produces working agent. | 2 | Todo
S053 | E13 | Select base for LoRA | researcher | an open-weights model appropriate for LoRA fine-tuning | parametric learning has a target | Pick among Qwen, Llama variants; document reasoning. | 1 | Todo
S054 | E13 | Training data pipeline | researcher | consolidated knowledge to be formatted for LoRA training | parametric updates are grounded | Script emits instruction-tuning format from semantic memory tier. | 3 | Todo
S055 | E13 | Retention-controlled update | researcher | LoRA updates bounded by KL divergence constraint | we don't overwrite core capabilities | Training loop enforces update norm bound; validated on held-out eval set. | 5 | Todo
S056 | E13 | A/B between checkpoints | researcher | to compare pre- and post-update behavior | verify learning without regression | Eval harness runs fixed set; regression >5% blocks promotion. | 2 | Todo

## Sprint 0 (4 weeks)
Week | Story IDs | Goal | Definition of Done
1 | S001, S002, S005, S006, S007, S008, S012, S013 | Stack up. OpenClaw + MemOS + Qdrant + Kuzu + OpenSpace all running locally via Docker Compose. | `docker compose up` brings everything up; CLI channel works; MemOS API responds.
2 | S003, S004, S009, S010, S011, S014, S015 | Wire the basics. Heartbeat fires on schedule. Memory recall/capture per turn via official plugin. Skill invocation works end-to-end. | At least one heartbeat-triggered test skill runs; a real conversation retrieves and writes memories; inspector CLI shows them.
3 | S016, S017, S018, S021, S022, S026, S027 | Curation + Rewire foundations. Salience gating, dedup, entity extraction, graph edge creation, skill quality tracking. | New turns score for salience; duplicates merge; entity graph grows; skill scores update after each invocation.
4 | S019, S020, S023, S028, S030, S034, S045, S047 | Close the loop. Contradiction handling with supersession. Reflection insights. Nightly consolidation. Decay scoring. Observability. | Synthetic contradiction test passes. Nightly job produces a semantic memory. Health check green. Policy logs emitted.

## Risks
Risk | Likelihood | Impact | Mitigation
OpenSpace license not as permissive as advertised | Low | High | Verify LICENSE file on GitHub before Sprint 0. Have Voyager-inspired fallback ready.
MemOS maturity — it's under a year old | Medium | High | Hide behind a thin interface; be prepared to swap for Letta or Mem0 (accept its open-core limits).
Kuzu feature gaps vs Neo4j | Medium | Medium | Kuzu covers our needs (nodes, edges, Cypher-like queries). If hit a wall, ArangoDB Apache 2.0 is the fallback.
Contradiction detection via LLM is expensive | High | Medium | Batch checks on heartbeat, not per-turn, for low-priority writes. Cache embeddings.
Heartbeat jobs drift / pile up | Medium | Medium | Idempotent job design; skip-if-running locks; metrics on job duration.
Skill explosion — too many low-quality skills | High | Medium | Deprecation policy + dedup at creation. Quality threshold for retrieval.
Parametric unlearning (E13) is research-grade | High | Low | Keep in P2. Don't block v0.1 on it.
Hyperscaler lock-in via managed services | Low | High | Stick to Docker containers; treat hyperscaler as dumb VM host until Phase 3.
User accidentally 'forget's something critical | Medium | Medium | 7-day grace window + audit log + undelete. Confirmation prompt on large-scope forgets.
Cost creep from LLM API calls | High | Medium | Route cheap calls (entity extraction, salience) to smaller/cheaper model; frontier only for reasoning.